## Participants
Inspection Roles
No | Group Member | Roles | Comment
1 | Trần Quang Hiếu | Inspector
2 | Huỳnh Đức Huy | Inspector
3 | Nguyễn Trung Kiên | Inspector
4 | Võ Hùng Cường | Inspector
5 | Bùi Thành Nghĩa | Moderator
6 | Team 3 | Author

## Schedules
Inspection Schedule
No | Task | Task owner | Start time | End time | Comment
1. | Divide the roles of each member within the team | Nghĩa | 2024-01-27 | 2024-01-27
2. | List the tools/resources used | Nghĩa | 2024-01-27 | 2024-01-27
3. | Receive materials from team 3 | Nghĩa | 2024-01-27 | 2024-01-27
4. | Make plan schedule for team | Nghĩa | 2024-01-27 | 2024-01-28
5. | Distribute documents to other members in the team | Nghĩa | 2024-01-27 | 2024-01-28
6. | Making check list | Nghĩa | 2024-01-28 | 2024-01-28
7. | Inspect Planning and Defined Process Document | Nghĩa | 2024-01-28 | 2024-01-28
8. | Inspect SRS Document | Hiếu | 2024-01-28 | 2024-01-28
9. | Inspect UI Design Document | Kiên | 2024-01-28 | 2024-01-28
10. | Inspect Code | Cường | 2024-01-28 | 2024-01-28
11. | Inspect Test-Case file | Huy | 2024-01-28 | 2024-01-28
12. | Fill in the Check list | Cường | 2024-01-28 | 2024-01-29
12. | Integration all inspection files | Nghĩa | 2024-01-28 | 2024-01-29
13. | Finish the first inspection | Nghĩa, Hiếu, Huy, Cường, Kiên | 2024-01-29 | 2024-01-29

## Materials
Inspection Material
No | Tool/Material | Quantity | Comment
1. | Defined Process Document | 1 | Nghĩa
2. | Project Plan Document | 1 | Nghĩa
3. | Software Requirement Specification Document | 1 | Hiếu
4. | User Interface Design Document | 1 | Kiên
5. | Code Java | 1 | Cường
6. | Test-Case | 1 | Huy